## Sheet1
|  | Dates: | Jan. 20-25 | Jan. 26-Feb. 1 | Feb. 2-8 | Feb. 9-15 | Feb. 16-22 | Feb. 23-Mar. 1 | Mar. 2-8 | Mar. 9-15 | Mar. 16-22 (SB) | Mar. 23-29 | Mar. 30-Apr. 5 | Apr. 6-12 | Apr. 13-19 | Apr. 20-26 | Apr. 27-30
CSE 1002 Quadcopter Competition Schedule (Tentative) -- Spring 2015
who | category | weeks for specific tasks
Kick-off
ALL |  | Overview & select teams (in class) | X
ALL |  | complete Gantt chart (tentative) | X
Build ELEV-8
ALL |  | learn to solder (in class) |  | X
ALL |  | soldering & heat shrink |  | X | X
|  | assemble booms |  |  | X | X
|  | assemble chassis |  |  | X | X
|  | configuring electronics |  |  |  | X
Learn to fly
ALL |  | practice flying toys | X | X | X | X
ALL |  | practice flying simulator |  | X | X | X | X
ALL |  | ELEV-8 tethered flights |  |  |  | X | X
ALL |  | ELEV-8 free flights |  |  |  |  | X | X | X
|  | ELEV-8 precision flights | [6 empty] | X | X | (X)
|  | ELEV-8 competition practice | [9 empty] | X | X | X | X
| Arduino programming | [11 empty] | X | X | X
ALL |  | Intro to Arduino (in class) |  |  | X
|  | further program. practice |  |  |  | X | X | X
|  | finalize sensor selection | [5 empty] | X | X | X
|  | done logging programming | [7 empty] | X | (X) | X
|  | done other progr. (if any) | [9 empty] | X | X | X
CAD
ALL |  | intro to CAD (in class) |  |  |  | X
promo video
SOPH |  | generic plan |  | X
SOPH |  | collect footage |  | X | X | X | X | X | X | X | (X) | X | X
SOPH |  | on-going editing, post it (due Apr. 9) |  |  |  | X |  | X |  | X |  |  | X | X
rotor protection
ALL |  | brainstorming (in class) |  |  |  | X
|  | build proto & final |  |  |  | X | X
|  | CAD documentation |  |  |  |  | X | X
multi-pilot
|  | finalize comp. pilot plans | [9 empty] | X
camera mount
ALL |  | brainstorming (in class) |  |  |  |  | X
|  | CAD |  |  |  |  | X | X | X
|  | 3-D printing, testing | [6 empty] | X | X | (X)
close-up imaging
ALL |  | brainstorming (in class) |  |  |  |  | X
|  | camera testing/selection |  |  | X | X | X | X | X
|  | practice flying task | [8 empty] | (X) | X | X | X | X
exploration
ALL |  | brainstorming | [5 empty] | X | X
|  | camera/sensor integration | [6 empty] | X | X | (X) | X
|  | practice flying task | [9 empty] | X | X | X | X
|  | practice mapping | [10 empty] | X | X
|  | practice data analysis | [11 empty] | X | X
unique capability
ALL |  | brainstorming | [5 empty] | X | X
|  | try multiple candidates? | [7 empty] | X | (X) | X
|  | final decision | [9 empty] | X
|  | final implementation | [9 empty] | X | X | X
report writing / slide generation
|  | PDR writing (due Feb. 28) |  |  |  |  | X | X
|  | CDR writing (due Mar. 31) | [8 empty] | (X) | X | X
ALL |  | oral report slides (due Apr. 16) | [10 empty] | X | X | X
|  | post-comp. writing (due Apr. 30) | [12 empty] | X | X | X
competition planning
ALL |  | brainstorm ground operations | [7 empty] | X | (X) | X
|  | refine ground operations | [8 empty] | (X) | X | X
|  | practice/finalize ground operations | [10 empty] | X | X | X
|  | practice delivering oral report | [11 empty] | X | X
post-competition data analysis
|  | mapping | [12 empty] | X | X | X
|  | data analysis | [12 empty] | X | X | X